# Statement of Work

V5 Ultimate — enterprise implementation services

| Field | Value |
| --- | --- |
| SOW number | SOW-[YYYY]-[NNN] |
| Customer | [Legal entity] |
| Supplier | S.G. Systems, LLC |
| Effective date | [Date] |
| Governing agreement | Master Subscription Agreement (v5ultimate.com/legal/msa) |
| Deployment addendum | On-Premises Licence Addendum (v5ultimate.com/legal/on-prem-addendum) — on-prem only |
| Term | Services complete on final go-live sign-off. Subscription / M&S renews annually per MSA / Addendum. |

# 1. Background

This Statement of Work ("SOW") is issued under the Master Subscription Agreement ("MSA") between Customer and S.G. Systems, LLC ("Supplier") and, for on-premises or private-cloud deployments, the On-Premises Licence Addendum. In any conflict, the order of precedence is: this SOW, the Addendum (if applicable), the MSA, the Terms of Service.

# 2. Scope of services

Supplier will deliver the implementation services described in the attached Enterprise Implementation Plan ("the Plan"), covering:

- Discovery and regulatory mapping across the sites listed in Schedule A.

- Infrastructure enablement (SaaS tenant, or on-prem/private-cloud installation).

- Configuration of workflows, roles, electronic signatures and master-record templates.

- Delivery of IQ / OQ documentation packs and test scripts; remote assistance during Customer execution.

- Pilot-site PQ support and train-the-trainer certification for Customer trainers.

- Rollout support for each subsequent site in Schedule A and 30-day hypercare per site.

- Transition to steady state and quarterly business reviews.

# 3. Deliverables

| # | Deliverable | Format | Acceptance |
| --- | --- | --- | --- |
| D1 | Regulatory strategy & site sequencing plan | PDF | Customer QA signature |
| D2 | Architecture & security review pack | PDF | Customer IT signature |
| D3 | IQ / OQ documentation pack and test scripts | PDF + scripts | Customer QA signs OQ report |
| D4 | Configured tenant / installed system (per site) | System access | PQ report signed |
| D5 | Train-the-trainer certificates | PDF | Per-trainer sign-off |
| D6 | Per-site go-live memo | PDF | Customer QA + site lead signature |
| D7 | Programme closure report | PDF | Steering committee acceptance |

# 4. Acceptance criteria

Each deliverable is deemed accepted when Customer signs the corresponding acceptance record or does not raise a written material defect within ten (10) business days of delivery. A "material defect" means a failure to conform to the criteria recorded against that deliverable in the Plan or in the OQ/PQ scripts.

# 5. Customer responsibilities

- Nominate a programme sponsor, QA lead and IT/security lead with authority to approve deliverables.

- Provide master records, SOPs, training matrices and integration specifications in machine-readable form.

- Execute IQ, OQ and PQ scripts in Customer environment(s), with Supplier remote assistance.

- Provide access to sites and systems required for rollout, on reasonable notice.

- Approve or reject deliverables within the acceptance window in §4.

# 6. Supplier responsibilities

- Assign a named programme lead and CSM for the duration of the engagement.

- Deliver the artefacts in §3 to the standards in the Plan.

- Provide 24/7 named escalation during hypercare and steady state.

- Maintain the deviation log and drive discrepancies to closure before each phase gate.

# 7. Fees & payment

| Item | Basis | Amount | Invoicing |
| --- | --- | --- | --- |
| Implementation services | Fixed fee | [Amount] | 25% on signature · 25% at OQ · 25% at pilot go-live · 25% at programme closure |
| Subscription (SaaS) | Per site / seat, annual | Per Order Form | Annually in advance |
| Licence + M&S (on-prem) | Per site, annual M&S renewal | Per Order Form | Annually in advance |
| Travel & expenses | At cost, pre-approved | T&E | Monthly, in arrears |

All fees are exclusive of applicable taxes. Payment terms per MSA §7 (Net 30 unless stated otherwise on the Order Form).

# 8. Change control

Changes to scope, deliverables, timeline or fees must be recorded in a written Change Request signed by both parties. Work under the Change Request begins only after signature. Emergency changes follow the fast-track procedure in the Plan.

# 9. Assumptions & dependencies

- Customer QA has decision authority on regulatory strategy and validation acceptance.

- Site infrastructure meets the On-Premises Deployment Specification (on-prem only).

- Supplier's IQ/OQ pack is the baseline; Customer-authored additions are Customer-owned.

- Programme duration assumes continuous access to Customer stakeholders per the RACI in the Plan.

# 10. Warranties & liability

Warranties, liability caps, indemnities, confidentiality and data-protection terms are governed by the MSA and, where applicable, the On-Premises Licence Addendum. Nothing in this SOW modifies those terms.

# 11. Schedules

## Schedule A — Sites in scope

| # | Site | Region | Go-live target |
| --- | --- | --- | --- |
| 1 | [Site — pilot] |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |

## Schedule B — Named contacts

| Role | Name | Email | Phone |
| --- | --- | --- | --- |
| Customer — Programme sponsor |  |  |  |
| Customer — QA head |  |  |  |
| Customer — IT / security lead |  |  |  |
| Supplier — Programme lead |  |  |  |
| Supplier — CSM |  |  |  |

# 12. Signatures

| Party | Name / Title | Signature | Date |
| --- | --- | --- | --- |
| For Customer |  |  |  |
| For S.G. Systems, LLC |  |  |  |