# Enterprise Implementation Plan

V5 Ultimate — multi-site programme for regulated manufacturers

| Field | Value |
| --- | --- |
| Customer | [Legal entity] |
| Programme sponsor (Customer) | [Name · Title · Email] |
| Programme lead (S.G. Systems) | [Name · Title · Email] |
| Deployment model | SaaS ☐ On-premises ☐ Private cloud ☐ |
| Regulatory scope | 21 CFR Part 11 ☐ EU Annex 11 ☐ ISO 13485 ☐ 21 CFR 820 ☐ EU MDR ☐ 21 CFR 210/211 ☐ BRCGS / SQF / FSMA 204 ☐ ISO 22716 / MoCRA ☐ Other: ______ |
| Sites in scope | [Site 1, Site 2, Site 3 …] |
| Programme duration (typical) | 6–12 months (30–45 days per site after pilot) |
| Document version | 0.1 draft |
| Last updated | [Date] |

# 1. Programme summary

This document is the master implementation plan for the V5 Ultimate enterprise rollout at [Customer]. It records scope, sequencing, RACI, milestones and acceptance criteria across all sites in scope. It is a working document — updated at each governance checkpoint and referenced from the Statement of Work.

# 2. Governance & RACI

## 2.1 Steering committee

- Meets monthly during rollout, quarterly at steady state.

- Members: Customer programme sponsor, Customer QA head, Customer IT/security lead, S.G. Systems programme lead, S.G. Systems CSM.

## 2.2 Change board

- Approves all changes to configuration, master records, and validated integrations after Phase 3.

- Chaired by Customer QA. S.G. Systems attends as advisor.

## 2.3 RACI (summary)

| Activity | Customer QA | Customer IT | S.G. Systems |
| --- | --- | --- | --- |
| Regulatory strategy & mapping | A / R | C | R / C |
| Infrastructure & network | I | A / R | C |
| Configuration & master records | A / R | C | R |
| IQ / OQ execution | A / R | C | R |
| PQ / user acceptance | A / R | R | C |
| Train-the-trainer delivery | A | I | R |
| Cutover & hypercare | A | R | R |
| Steady-state release cadence | A | C | R |

Legend: R = Responsible · A = Accountable · C = Consulted · I = Informed

# 3. Phased delivery

## Phase 01 — Discovery & regulatory mapping (Weeks 1–2)

### Scope

- Site inventory, product families, master-record inventory, integration inventory.

- Regulatory strategy: Part 11 / Annex 11 posture, applicable standards, notified-body considerations.

- Data model workshop — batch, product, spec, deviation, CAPA, training.

### Sign-off gate

- Signed Regulatory Strategy document.

- Signed Site Sequencing plan.

## Phase 02 — Infrastructure & security (Weeks 3–4)

### Scope

- SaaS: tenant provisioned, SSO/SCIM wired, IP allow-lists, data residency confirmed.

- On-prem / private cloud: infrastructure sized per the On-Premises Deployment Specification, appliance images delivered signed and offline-capable.

- Security review pack: SOC 2, pen-test summary, DPIA inputs, sub-processor list.

### Sign-off gate

- Customer IT / security sign-off on architecture and security review.

## Phase 03 — Configuration & validation (Weeks 5–10)

### Scope

- Configure roles, workflows, electronic signatures, master-record templates.

- Author and execute IQ (installation) and OQ (operational) against the delivered test scripts.

- Deviation log maintained; every discrepancy tracked to closure before PQ.

### Sign-off gate

- Customer QA signs OQ report. Master-record revision baseline locked.

## Phase 04 — Pilot site + train-the-trainer (Weeks 11–14)

### Scope

- Pilot at Site 1: PQ (performance qualification) with production-representative batches.

- Train-the-trainer: certify 2–4 Customer trainers per region.

- Cutover playbook: fallback plan, comms, day-1 support roster.

### Sign-off gate

- Customer QA signs PQ report. Go-live decision recorded.

## Phase 05 — Rollout & hypercare (30–45 days per additional site)

### Scope

- Repeat abbreviated IQ/OQ/PQ at each subsequent site. Regression pack re-run against locked master records.

- 30-day hypercare per site: named engineer, daily standup, 24-hour issue turnaround.

### Sign-off gate

- Per-site go-live memo signed by Customer QA and local site lead.

## Phase 06 — Steady state

### Scope

- Quarterly business reviews. Release cadence aligned to change board.

- SaaS: subscription includes validated patches and regulatory updates (Part 11, Annex 11, evolving standards).

- On-prem: annual Maintenance & Support renewal delivers the same updates plus refreshed IQ/OQ documentation packs.

- 24/7 named escalation. Regulator / notified-body access on request.

# 4. Milestones & dates

| Milestone | Owner | Planned date | Actual |
| --- | --- | --- | --- |
| Kickoff | Programme leads |  |  |
| Regulatory strategy signed | Customer QA |  |  |
| Architecture signed | Customer IT |  |  |
| OQ signed | Customer QA |  |  |
| Pilot PQ signed | Customer QA |  |  |
| Site 2 go-live | Site lead |  |  |
| Site N go-live | Site lead |  |  |
| Steady state entry | Steering committee |  |  |

# 5. Risks & assumptions

### Assumptions

- Customer supplies existing master records, SOPs and training matrices in a machine-readable form.

- Customer QA has authority to sign IQ, OQ and PQ reports without external escalation.

- Site infrastructure meets the On-Premises Deployment Specification (on-prem only).

### Open risks

| Risk | Impact | Mitigation | Owner |
| --- | --- | --- | --- |

# 6. Change control

Any change to scope, configuration baseline or validated integrations after Phase 3 sign-off must be raised as a Change Request, reviewed by the change board, and re-validated before deployment. Emergency changes follow the fast-track procedure recorded in the SOP pack.

# 7. Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Customer — Programme sponsor |  |  |  |
| Customer — QA head |  |  |  |
| Customer — IT / security lead |  |  |  |
| S.G. Systems — Programme lead |  |  |  |